## Sheet1
Task: | Responsible Engineer: | Column1 | 14-Apr | 23-Apr | 24-Apr | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | KEY:
Project Proposal | Ryan | Column1: Done On Schedule? | Colors | Class Days: | Functional Prototype Due date
GANNT Chart | Calvin | Column1: YES | Ryan |  |  | 0 | 0 | 0
Work Breakdown Structure | Calvin | Column1: YES | Calvin |  |  | 0 | 0 | 0
[30 empty] | 1 | 0 | 1
Accelerometer (SPI) | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Initalize/Code | Ryan | Column1: YES | Number tasks Completed : | 28 |  | 0 | 0 | 0
Test | Ryan | Column1: YES | Number of tasks Completed on time: | 28 |  | 1 | 0 | 1
Light Detection Sensor | Calvin | Column1: YES | Number of tasks Completed Late: | 0 |  | 1 | 0 | 1
Build Circuit/Solder | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Initalize/Code | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Test light sensor | Calvin | Column1: YES | Percentage On time | 100% |  | 1 | 0 | 1
Motion Detection Sensor | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Build Circuit/Solder | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Initalize/Code | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Test Motion Detection | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Ultrasonic Sensor | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Initalize/Code | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Calculate distance/Send Data | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Test Ultrasonic Sensor | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
LCD | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Inmplement Code from Lab | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
[30 empty] | 1 | 0 | 1
Buzzer (PWM) | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Build Circuit/Solder | Calvin | Column1: YES |  |  |  | 0 | 0 | 0
Initalize/Code | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
Test Buzzer | Calvin | Column1: YES |  |  |  | 1 | 0 | 1
LED Matrix | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Build Circuit/Solder | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Initalize/Code | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Test LED Matrix | Ryan | Column1: YES |  |  |  | 1 | 0 | 1
Implement Code Together | [29 empty] | 1 | 0 | 1 | bar: 2025-05-08 to 2025-05-11
Light Sensor-Turn off Sleep mode | Calvin | [28 empty] | 1 | 0 | 1 | bar: 2025-05-08 to 2025-05-11
Motion-Ultra-LCD | Ryan | [28 empty] | 0 | 0 | 0 | bar: 2025-05-08 to 2025-05-11
Ultra-LED-Buzzer | Ryan | Column1: YES |  |  |  | 0 | 0 | 0
Accelerometer - LED-Buzzer | Ryan | [28 empty] | 0 | 0 | 0 | bar: 2025-05-08 to 2025-05-11
Test | [29 empty] | 1 | 0 | 1 | bar: 2025-05-12 to 2025-05-14
"shake" test | Calvin | [28 empty] | 0 | 0 | 0 | bar: 2025-05-12 to 2025-05-14
Functional prototype | Ryan | [28 empty] | 0 | 0 | 0 | bar: 2025-05-12 to 2025-05-14
[30 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0
[30 empty] | 0 | 0 | 0